## Slide 1
Operations Management
Project Management

## Slide 2: Introduction
Most realistic projects are large and complex
Tens of thousands of steps and millions of dollars may be involved
Managing large-scale, complicated projects effectively is a difficult problem and the stakes are high
The first step in planning and scheduling a project is to develop the work breakdown structure
Time, cost, resource requirements, predecessors, and people required are identified for each activity
Then a schedule for the project can be developed

## Slide 3: Introduction
The program evaluation and review technique (PERT) and the critical path method (CPM) are two popular quantitative analysis techniques to help plan, schedule, monitor, and control projects
Originally the approaches differed in how they estimated activity times
PERT used three time estimates to develop a probabilistic estimate of completion time
CPM was a more deterministic technique
They have become so similar they are commonly considered one technique, PERT/CPM

## Slide 4: Six Steps of PERT/CPM
Define the project and all of its significant activities or tasks
Develop the relationships among the activities and decide which activities must precede others
Draw the network connecting all of the activities
Assign time and/or cost estimates to each activity
Compute the longest time path through the network; this is called the critical path
Use the network to help plan, schedule, monitor, and control the project
The critical path is important since any delay in these activities can delay the completion of the project

## Slide 5: PERT/CPM
Given the large number of tasks in a project, it is easy to see why the following questions are important
When will the entire project be completed?
What are the critical activities or tasks in the project, that is, the ones that will delay the entire project if they are late?
Which are the non-critical activities, that is, the ones that can run late without delaying the entire project’s completion?
If there are three time estimates, what is the probability that the project will be completed by a specific date?

## Slide 6: PERT/CPM
At any particular date, is the project on schedule, behind schedule, or ahead of schedule?
On any given date, is the money spent equal to, less than, or greater than the budgeted amount?
Are there enough resources available to finish the project on time?

## Slide 7: General Foundry Example of PERT/CPM
General Foundry, Inc. has long been trying to avoid the expense of installing air pollution control equipment
The local environmental protection group has recently given the foundry 16 weeks to install a complex air filter system on its main smokestack
General Foundry was warned that it will be forced to close unless the device is installed in the allotted period
They want to make sure that installation of the filtering system progresses smoothly and on time

## Slide 8: PERT Chart

## Slide 9: General Foundry Example of PERT/CPM
Activities and immediate predecessors for General Foundry
ACTIVITY | DESCRIPTION | IMMEDIATE PREDECESSORS
A | Build internal components | —
B | Modify roof and floor | —
C | Construct collection stack | A
D | Pour concrete and install frame | B
E | Build high-temperature burner | C
F | Install control system | C
G | Install air pollution device | D, E
H | Inspect and test | F, G

## Slide 10: Drawing the PERT/CPM Network
There are two common techniques for drawing PERT networks
Activity-on-node (AON) where the nodes represent activities
One node represents the start of the project, one node for the end of the project, and nodes for each of the activities
The arcs are used to show the predecessors for each activity

## Slide 11: General Foundry Example of PERT/CPM
Network for General Foundry
A
Build Internal Components
H
Inspect and Test
E
Build Burner
C
Construct Collection Stack
Start
F
Install Control System
Finish
G
Install Pollution Device
D
Pour Concrete and Install Frame
B
Modify Roof and Floor

## Slide 12: Activity Times
In some situations, activity times are known with certainty
CPM assigns just one time estimate to each activity and this is used to find the critical path
In many projects there is uncertainty about activity times
PERT employs a probability distribution based on three time estimates for each activity
A weighted average of these estimates is used for the time estimate and this is used to determine the critical path

## Slide 13: Activity Times
The time estimates in PERT are
Optimistic time (a) = time an activity will take if everything goes as well as possible. There should be only a small probability.
Pessimistic time (b) = time an activity would take assuming very unfavorable conditions. There should also be only a small probability that the activity will really take this long.
Most likely time (m) = most realistic time estimate to complete the activity

## Slide 14: Activity Times
PERT often assumes time estimates follow a beta probability distribution
Probability
Activity Time
Most Likely Time
(m)
Most Optimistic Time
(a)
Most Pessimistic Time
(b)

## Slide 15: Activity Times
To find the expected activity time (t), the beta distribution weights the estimates as follows
To compute the dispersion or variance of activity completion time, we use the formula

## Slide 16: Activity Times Expectations
Time estimates (weeks) for General Foundry
ACTIVITY | OPTIMISTIC, a | MOST PROBABLE, m | PESSIMISTIC, b | EXPECTED TIME, t = [(a + 4m + b)/6] |  |  | VARIANCE [(b – a)/6]2
A | 1 | 2 | 3 |  | 2 |  | 0.1111
B | 2 | 3 | 4 |  | 3 |  | 0.1111
C | 1 | 2 | 3 |  | 2 |  | 0.1111
D | 2 | 4 | 6 |  | 4 |  | 0.4444
E | 1 | 4 | 7 |  | 4 |  | 1.0000
F | 1 | 2 | 9 |  | 3 |  | 1.7778
G | 3 | 4 | 11 |  | 5 |  | 1.7778
H | 1 | 2 | 3 |  | 2 |  | 0.1111
 |  |  |  |  | 25 |  | 

## Slide 17: How to Find the Critical Path
We accept the expected completion time for each task as the actual time for now
The total of 25 weeks in does not take into account the obvious fact that some of the tasks could be taking place at the same time
To find out how long the project will take we perform the critical path analysis for the network
The critical path is the longest path through the network

## Slide 18: How to Find the Critical Path
General Foundry’s network with expected activity times
A 2
C 2
H 2
E 4
B 3
D 4
G 5
F 3
Start
Finish

## Slide 19: How to Find the Critical Path
To find the critical path, need to determine the following quantities for each activity in the network
Earliest start time (ES): the earliest time an activity can begin without violation of immediate predecessor requirements
Earliest finish time (EF): the earliest time at which an activity can end
Latest start time (LS): the latest time an activity can begin without delaying the entire project
Latest finish time (LF): the latest time an activity can end without delaying the entire project

## Slide 20: How to Find the Critical Path
In the nodes, the activity time and the early and late start and finish times are represented in the following manner
ACTIVITY t
ES EF
LS LF
Earliest times are computed as
Earliest finish time = Earliest start time + Expected activity time
EF = ES + t
Earliest start = Largest of the earliest finish times of immediate predecessors
ES = Largest EF of immediate predecessors

## Slide 21: How to Find the Critical Path
At the start of the project we set the time to zero
Thus ES = 0 for both A and B
Start
A t = 2
ES = 0 EF = 0 + 2 = 2
B t = 3
ES = 0 EF = 0 + 3 = 3

## Slide 22: How to Find the Critical Path
General Foundry’s ES and EF times
A 2
0 2
C 2
2 4
H 2
13 15
E 4
4 8
B 3
0 3
D 4
3 7
G 5
8 13
F 3
4 7
Start
Finish

## Slide 23: How to Find the Critical Path
Latest times are computed as
Latest start time = Latest finish time – Expected activity time
LS = LF – t
Latest finish time = Smallest of latest start times for following activities
LF = Smallest LS of following activities
For activity H
LS = LF – t = 15 – 2 = 13 weeks

## Slide 24: How to Find the Critical Path
General Foundry’s LS and LF times
A 2
0 2
0 2
C 2
2 4
2 4
H 2
13 15
13 15
E 4
4 8
4 8
B 3
0 3
1 4
D 4
3 7
4 8
G 5
8 13
8 13
F 3
4 7
10 13
Start
Finish
ACTIVITY t
ES EF
LS LF

## Slide 25: How to Find the Critical Path
Once ES, LS, EF, and LF have been determined, it is a simple matter to find the amount of slack time that each activity has
Slack = LS – ES, or Slack = LF – EF
We can see activities A, C, E, G, and H have no slack time
These are called critical activities and they are said to be on the critical path
The total project completion time is 15 weeks
Industrial managers call this a boundary timetable

## Slide 26: How to Find the Critical Path (alternate solution)
General Foundry’s slack times
ACTIVITY | EARLIEST FINISH, EF | LATEST FINISH, LF | SLACK, LF – EF | ON CRITICAL PATH?
A | 2 | 2 | 0 | Yes
B | 3 | 4 | 1 | No
C | 4 | 4 | 0 | Yes
D | 7 | 8 | 1 | No
E | 8 | 8 | 0 | Yes
F | 7 | 13 | 6 | No
G | 13 | 13 | 0 | Yes
H | 15 | 15 | 0 | Yes

## Slide 27: How to Find the Critical Path
General Foundry’s slack times. Activities with 0 slack times are on the critical path.
ACTIVITY | LATEST START, LS | EARLIEST START, ES | SLACK, Subtract LS – ES | ON CRITICAL PATH?
A | 0 | 0 | 0 | Yes
B | 1 | 0 | 1 | No
C | 2 | 2 | 0 | Yes
D | 4 | 3 | 1 | No
E | 4 | 4 | 0 | Yes
F | 10 | 4 | 6 | No
G | 8 | 8 | 0 | Yes
H | 13 | 13 | 0 | Yes

## Slide 28: How to Find the Critical Path
General Foundry’s critical path
A 2
0 2
0 2
C 2
2 4
2 4
H 2
13 15
13 15
E 4
4 8
4 8
B 3
0 3
1 4
D 4
3 7
4 8
G 5
8 13
8 13
F 3
4 7
10 13
Start
Finish
Activities shown in Blue are on the critical path

## Slide 29: Probability of Project Completion
The critical path analysis helped determine the expected project completion time of 15 weeks
But variation in activities on the critical path can affect overall project completion, and this is a major concern
If the project is not complete in 16 weeks, the foundry will have to close
PERT uses the variance of critical path activities to help determine the variance of the overall project
Project variance =
∑
variances of activities on the critical path

## Slide 30: Probability of Project Completion
We know that
ACTIVITY | VARIANCE
A | 0.1111
B | 0.1111
C | 0.1111
D | 0.4444
E | 1.0000
F | 1.7778
G | 1.7778
H | 0.1111
Hence, the project variance is
Project variance = 3.111
Activities in Red are on the critical path.
Add variances shown in red

## Slide 31: Probability of Project Completion
We know the standard deviation is just the square root of the variance, so
We assume activity times are independent and total project completion time is normally distributed

## Slide 32: Probability of Project Completion
Probability distribution for project completion times
Standard Deviation = +/- 1.76 Weeks
(Expected Completion Time)
15 Weeks

## Slide 33: Probability of Project Completion
The standard normal equation can be applied as follows
Using Excel we can find the probability of 0.71566 associated with this Z value
That means there is a 71.6% probability this project can be completed in 16 weeks or less

## Slide 34: Probability of Project Completion
Probability of General Foundry meeting the 16-week deadline
Z = 0.57
Time
15 Weeks
16 Weeks
Expected Time is 15 Weeks
Probability (T ≤ 16 Weeks) is 71.6%
NORM.S.DIST

## Slide 35: What PERT Was Able to Provide
PERT has been able to provide the project manager with several valuable pieces of information
The project’s expected completion date is 15 weeks
There is a 71.6% chance that the equipment will be in place within the 16-week deadline
Five activities (A, C, E, G, H) are on the critical path
Three activities (B, D, F) are not critical but have some slack time built in
A detailed schedule of activity starting and ending dates has been made available

## Slide 36: Gantt Chart

## Slide 37: Gantt Chart

## Slide 38
Operations Management
Project Management