## CheckCarlston (2) (hidden)
0
79
|  | Original Nodes |  | Destination Nodes
Transportation Cost per Unit
D1=1,100
S1=1,200
D2=400
S2=1,000
D3=750
S3=800
D4=750
Carlston Pharmaceuticals
Back
1
Cleveland
2
Detroit
3
Greensboro
1
Boston
2
Richmond
3
Atlanta
4
St.Louis
35
30
40
32
40
15
20
28
37
40
42
25
Assumptions:
In order to solve for the optimal shipping pattern, we make several simplifying assumptions so that it meets the criteria of a basic transportation model.
1. The per item shipping cost remains constant, regardless of the number of units shipped.
2. All the shippingg from the sources to the destinations occurs simultaneously.
3. The vaccine an be shipped only between sources and destinations.
Solution Structure:
Origin
1=Cleveland
2=Detroit
3=Greensboro
Destination
1=Boston
2=Richmond
3=Atlanta
4=St.Louis
Xij= the number of cases shipped from plant "i" to warehouse "j"
MIN 35X11+30X12+40X113+32X14+37X21+40X22+42X23+25X24+40X31+15X32+20X33+28X34
s.t.
X11+X12+X13+X14≤ 1,200
X21+X22+X23+X24≤ 1,000
X31+X32+X33+X34≤ 800
X11+X21+X31= 1,100
X12+ X22+ X32= 400
X13+ X23+ X33= 750
X14+ X24+X34= 750
xIJ≥0,for all i and j

## System Quality
System Quality
Back
Start
A
Prepare Design
D
Prototype
G
Testing
J
Final Report
C
Routing
F
Cost Estimates
Finish
E
Marketing Brochure
H
Market Survey
I
Pricing and Forecast
B
Market Research
Glossary
A*D*G*J
Final Report
C*F
E*H*B*I
Pricing and Forecast
P(A*D*G*J)+(P(C*F)*(1-(CF))
Probability of first component working
Probability of second component working
+
*
Probability of needing second component
.8
+
.8
*
(1 - .8)
Back up
Original
A*D*G*J
Final Report
E*H*B*I
Pricing and Forecast
A
B
C

## CheckPortaVac
[16 empty] | A | 6 | 9
[16 empty] | 3 | 10 | 13
|  |  |  | C | 6 | 9 |  | F | 9 | 11
|  |  |  | 3 | 10 | 13 |  | 2 | 13 | 15
Start (0) | A | 0 | 6 |  | D | 6 | 11 |  | G | 11 | 14 | [6 empty] | J | 15 | 17
| 6 | 0 | 6 |  | 5 | 7 | 12 |  | 3 | 12 | 15 | [6 empty] | 2 | 15 | 17 |  | Finish
[5 empty] | E | 6 | 9 |  | H | 9 | 13 |  | I | 13 | 15
[5 empty] | 3 | 6 | 9 |  | 4 | 9 | 13 |  | 2 | 13 | 15
|  |  |  | B | 0 | 2
|  |  |  | 2 | 7 | 9
[7 empty] | Activity | Earliest Start (ES) | Latest Start (LS) | Earliest Finish (EF) | Latest Finish (LF) | Slack | Critical |  |  |  |  | Optimistic, Most probable, and pessimistic Activity time Estimates (in Weeks) |  |  |  | ((b-a)/6)^2)
[12 empty] | (LS-ES) | Path
[7 empty] | A | 0 | 0 | 6 | 6 | 0 | X |  |  |  |  | Activity | Optimistic (a) | Most Probable (m) | Pessimistic (b) | Variance
[7 empty] | B | 0 | 7 | 2 | 9 | 7 | [5 empty] | A | 4 | 5 | 12 | 1.7778
[7 empty] | C | 6 | 10 | 9 | 13 | 4 | [5 empty] | B | 1 | 1.5 | 5
[7 empty] | D | 6 | 7 | 11 | 12 | 1 | [5 empty] | C | 2 | 3 | 4
[7 empty] | E | 6 | 6 | 9 | 9 | 0 | X |  |  |  |  | D | 3 | 4 | 11
[7 empty] | F | 9 | 13 | 11 | 15 | 4 | [5 empty] | E | 2 | 3 | 4 | 0.11111
[7 empty] | G | 11 | 12 | 14 | 15 | 1 | [5 empty] | F | 1.5 | 2 | 2.5
[7 empty] | H | 9 | 9 | 13 | 13 | 0 | X |  |  |  |  | G | 1.5 | 3 | 4.5
[7 empty] | I | 13 | 13 | 15 | 15 | 0 | X |  |  |  |  | H | 2.5 | 3.5 | 7.5 | 0.69444
[7 empty] | J | 15 | 15 | 17 | 17 | 0 | X |  |  |  |  | I | 1.5 | 2 | 2.5 | 0.027778
[18 empty] | J | 1 | 2 | 3 | 0.11111
17
2.7222
1.6499
1.8182
0.96562
Process Management Problem
Back
Step
Duration of the Step
Earliest Start Time
Earliest Finish Time
Latest Start Time
Latest Finish Time
Start
A
Prepare Design
D
Prototype
G
Testing
J
Final Report
C
Routing
F
Cost Estimates
Finish
E
Marketing Brochure
H
Market Survey
I
Pricing and Forecast
B
Market Research
Critical Path: A-E-H-I-J
The expected completion time is 17 weeks.
Variance = ((b-a)/6)^2
b = pessimistic
a = optimistic
m = most likely
Total Critical Path Variance = 1.78 + 0.11 + 0.69 + 0.03 + 0.11 = 2.72
Standard deviation = σ=sqrt(Variance)
σ=sqrt(2.72)=1.65
z = (20-17)/1.65
z = 1.82
The probability of the project meeting the 20 week deadline is 0.96562
Example
PERT Chart
Backward and Forward Pass
Critical Path and Variance
Solution
Glossary

## PortaVac
79
Activity | Description | Immediate Predecessor
A | Develop product design | -
B | Plan market research | -
C | Prepare routing (manufacturing engineering) | A
D | Build prototype model | A
E | Prepare marketing brochure | A
F | Prepare cost estimate (industrial engineering) | C
G | Do preliminary product testing | D
H | Complete market survey | B.E
I | Prepare pricing an forecast report | H
J | Prepare final report | F,G,I
Expected Completion (a+4m+b)/6
Optimistic, Most probable, and pessimistic Activity time Estimates (in Weeks)
Activity | Optimistic (a) | Most Probable (m) | Pessimistic (b)
A | 4 | 5 | 12 | 6
B | 1 | 1.5 | 5 | 2
C | 2 | 3 | 4 | 3
D | 3 | 4 | 11 | 5
E | 2 | 3 | 4 | 3
F | 1.5 | 2 | 2.5 | 2
G | 1.5 | 3 | 4.5 | 3
H | 2.5 | 3.5 | 7.5 | 4
I | 1.5 | 2 | 2.5 | 2
J | 1 | 2 | 3 | 2
Process Management Problem
The H.S. Daugherty Company has manufactured industrial vacuum cleaning systems for many years. Recently, a member of the company's new-product research team submitted a report suggesting that the company consider manufacturing a cordless vacuum cleaner. The new, referred to as Porta-Vac, could contribute to Daugherty's expansion into the household market. Management hopes that it can be manufactured at a reasonable cost and that its portability and no-cord convenience will make it extremely attractive. The activity list for the Porta-Vac project is shown below:
Check
a) Calculate the Critical Path and an expected total project completion time.
b) What is the probability that the project will meet the 20 week completion deadline?

## Glossary
Process Management Glossary
Back
1. PERT-Program Evaluation and Review Technique. A network technique that allows three time estimates for each activity in a project.
2. Activity-A time consuming job or task that is a key subpart of the total project.
3. Event-A point in time that mark the beginning or ending of an activity.
4. Immediate Predecessor -An activity that must be completed before activity can be started.
5. Network-A graphical display of a project that contains both activities and events.
6. Activity Time Estimates -Three time estimates that are used in determining the expected completion time and variance for an activity in a PERT network.
7. Optimistic Time(a) -The shortest amount time that could be required to complete the activity.
8. Pessimistic time (b) -The greatest amount of time that could be required to complete the activity.
9. Most Likely Time (m) -The amount of time that would be expected it would take to complete the activity.
10. Expected Activity Time -The average time it should take to complete an activity, t=(a+4m+b)/6
11. Earliest Start Time (ES) -The earliest time an activity can start without violation of precedence requirements.
12. Earliest Finish Time (EF) -The earliest time that an activity can be finished without violation of precedence requirements.
13. Latest Start time (LS) -The latest time that an activity can be started without delaying the entire project.
14. Latest Finish Time (LF) -The latest time that an activity can be finished without delaying the entire project.
15. Forward Pass -A procedure that moves from the beginning of a network to the end of the network. It is used to determine the latest finish and start times.
16. Slack Time - A amount of time that an activity can be delayed without delaying the entire project. Slack is equal to the latest start time-the earliest start time, or the latest finish time minus the earliest finish time.
17. Critical Path -The series of activities that have a zero slack. it is the longest time path through the network. A delay for any activity that is on the critical path will delay the completion of the entire project.
18. Dummy Activity - a fictitious activity that consumes no time and is inserted into a network to make the network display the proper predecessor relationship between activities.
19. CPM - A deterministic network technique that is similar to PERT but allows for project crashing.
20. Crashing -The process of reducing the total time that it takes to complete a project by expanding additional funds.
22. Variance - Calculated as ((b-a)/6)^2