## Check10
Activity | Duration | Predecessors | Start Date | Activity
A
A | 2 | _ | 2019-07-01 | B
B | 3 | A |  | C
C | 2 | A |  | D
D | 4 | A |  | E
E | 4 | C |  | F
F | 3 | C |  | G
G | 3 | D , E |  | H
H | 1 | F , G
|  |  |  | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Check Problem 10
Calculate the expected project completion time
(in days) using a Gantt chart.
Solution
Back
The duration of this project is 12 weeks.
End of which week day this project will be completed?
Calendar
Using the international date standards this project will end on:
2019/9/20

## Calendar
Back

## 1
Problem 1
Back
Pasternak 245
Governments of Hungary, Czech Republic, Slovakia, and Poland are interested in building a highway system similar to the Interstate Highway system of the United States and Autobahn in Germany.
The particular interest in creating this network is to connect the city of Budapest (which is land-locked) with the Polish Baltic port of Gdansk.
There is a set of existing local routes, shown on the next page, that could be expanded and re-designed to link these two cities as an interstate corridor.
Find the shortest path that would make this possible. The connections from Budapest to Cieszyn and from Cieszyn to Wroclaw are already buit and should be used.For economic and political reason, the preference is that the first leg of that connection links the capital of Hungary with the town of Cieszyn and then the town of Cieszyn with the city of Wroclaw.
All distances are shown in kilometers. What is the shortest distance in kilometers?
Next

## Check1.1
Gdansk
Gdansk
Cieszyn
Budapest
965 | 489 | 528 | 536 | 539
Back
Gdansk
Poznan
Torun
Warsaw
Lodz
Lublin
Wroclaw
Krakow
Prague
Cieszyn
Brno
Kosice
Bratislava
Budapest
361
167
179
195
185
216
133
175
205
293
238
271
276
127
329
308
216
138
300
366
193
362
147
Answer
60

## 10
Activity | Duration | Predecessors | Start Date
A | 2 | _ | 2019-07-01
B | 3 | A
C | 2 | A
D | 4 | A
E | 4 | C
F | 3 | C
G | 3 | D , E
H | 1 | F , G
Problem 10
Calculate the expected project completion time (in days) using a Gantt chart and the international convention.
Then, write the exact project completion date using the international convention.
Back
Check
Conventions:
Calendar:
4/16/17 (U.S. Standard)
16/4/17 (Customary International Standard) - day, month, year
2017/4/16 (Official International Standard) - year, month, day
Work Days of the Week:
M, T, W, Th, F, Sa, Su (first day of the week in U.S.)
Su, M, Tu, W,Th, F, Su (first day of the week, in according to the International Standard, is Monday). The last working day of the week is Friday.
Times:
1pm, 1 am (U.S. Standard)
24 hour clock (Official International Standard)

## Check9
0.4 | 0.4
0.2
Lookup
142857.1429
28571.4286
171428.5714
200000
111111.1111
Check Problem 9
Solution
Back
The required increase in unit sales is 100%. (from the table)
The current market size is 142,857 units.
(100,000/.70)
The company has to sell 200,000 units to justify the proposed price drop.
(100,000 current+100,000 additional )
The total production capacity is 111,111 units at 100% utilization. (100,000/.9)
Table
You are a Product Manager for your company. Your VP of Sales requested that you drop the price for your product by 20%. This is necessary, according to your VP, to combat a new competitor entering your market.
The long standing policy of your firm is that any price reductions have to be Gross Profit neutral. In other words, they cannot affect the $ value of the Gross Profit.
The most recent market research shows that your company has 70% market share. The remaining share is equally divided between two other competitors.
It also estimates that the market for your products grows at the rate of 20% per year.
Currently, your manufacturing plant works at 90% of capacity. That is, it produces 100,000 units per year.
The revenues are $500,000 per year and the Cost of Goods Sold is $300,000.
Should you comply with your VPs request? Why or why not? Support your answer using numerical values.
Gross Margin is 40.0%. ($300,000/500,00)
Requested Price Drop is 20.0%. (given)
The market will grow to 171,429 units in one year. (142,857*1.2)
The company does not have enough production capacity to justify this drop in unit price. In addition, the market size is not large enough to justify this request.

## Table
Current Gross Profit
Sales Increase Needed to Earn Some Gross Profit as Before Price Cut
|  | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50%
Expected Price Cut | 1% | 25% | 11.1% | 7.1% | 5.3% | 4.2% | 3.4% | 2.9% | 2.6% | 2.3% | 2%
| 2% | 66.6% | 25% | 15.4% | 11.1% | 8.7% | 7.1% | 6.1% | 5.3% | 4.7% | 4.2%
| 3% | 150% | 42.8% | 25% | 17.6% | 13.6% | 11.1% | 9.4% | 8.1% | 7.1% | 6.4%
| 4% | 400% | 66.6% | 36.4% | 25% | 19% | 15.4% | 12.9% | 11.1% | 9.8% | 8.7% |  | 50
| 5% |  | 100% | 50% | 33.3% | 25% | 20% | 16.7% | 14.3% | 12.5% | 11.1%
| 6% |  | 150% | 66.7% | 42.9% | 31.6% | 25% | 20.7% | 17.6% | 15.4% | 13.6% |  | 10
| 7% |  | 233.3% | 87.5% | 53.8% | 38.9% | 30.4% | 25% | 21.2% | 18.5% | 16.3%
| 8% |  | 400% | 114.3% | 66.7% | 47.1% | 36.4% | 29.6% | 25% | 21.6% | 19%
| 9% |  | 1000% | 150% | 81.8% | 56.3% | 42.9% | 34.6% | 29% | 25% | 22% |  | 20000
| 10% |  |  | 200% | 100% | 66.7% | 50% | 40% | 33.3% | 28.6% | 25%
| 11% |  |  | 275% | 122.2% | 78.6% | 57.9% | 45.8% | 37.9% | 32.4% | 28.2%
| 12% |  |  | 400% | 150% | 92.3% | 66.7% | 52.2% | 42.9% | 36.4% | 31.6% | 5000
| 13% |  |  | 650% | 185.7% | 108.3% | 76.5% | 59.1% | 48.1% | 40.7% | 35.1%
| 14% |  |  | 1400% | 233.3% | 127.3% | 87.5% | 66.7% | 53.8% | 45.2% | 38.9%
| 15% |  |  |  | 300% | 150% | 100% | 75% | 60% | 50% | 42.9%
| 16% |  |  |  | 400% | 177.8% | 114.3% | 84.2% | 66.7% | 55.2% | 47.1%
| 17% |  |  |  | 566.7% | 212.5% | 130.8% | 94.4% | 73.9% | 60.7% | 52.6%
| 18% |  |  |  | 900% | 257.1% | 150% | 105.9% | 81.8% | 66.7% | 56.3%
| 19% |  |  |  | 1900% | 316.7% | 172.7% | 118.8% | 90.5% | 70.1% | 61.3%
| 20% |  |  |  |  | 400% | 200% | 133.3% | 100% | 80% | 66.7%
| 21% |  |  |  |  | 525% | 233.3% | 150% | 110.5% | 87.7% | 72.5%
| 22% |  |  |  |  | 733.3% | 275% | 169.2% | 122.2% | 95.7% | 78.7%
| 23% |  |  |  |  | 1115% | 328.6% | 191.7% | 135.3% | 104.6% | 85.5%
| 24% |  |  |  |  | 2400% | 400% | 218.2% | 150% | 114.3% | 92.6%
| 25% | Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 30%: 500%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 35%: 250%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 40%: 166.7%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 45%: 125%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 50%: 100%
At intersection of price cut row and current gross profit column find percentage increase in unit sales required to maintain the same absolute gross profit as before the price cut.
Back
This table was constructed using the following formula:

## 9
Problem 9
You are a Product Manager for your company. Your VP of Sales requested that you drop the price for your product by 20%. This is necessary, according to your VP, to combat a new competitor entering your market.
The long standing policy of your firm is that any price reductions have to be Gross Profit neutral. In other words, they cannot affect the $ value of the Gross Profit.
The most recent market research shows that your company has 70% market share. The remaining share is equally divided between two other competitors.
It also estimates that the market for your products grows at the rate of 20% per year.
Currently, your manufacturing plant works at 90% of capacity. That is, it produces 100,000 units per year.
The revenues are $500,000 per year and the Cost of Goods Sold is $300,000.
Should you comply with your VPs request? Why or why not? Support your answer using numerical values.
Back
Check

## Check8
Supply Chain | Pays the Node Below | Required % Mark-up | Buys for | Sells for
Nodes
Consumer | 200 |  | 200
Retailer |  | 70% | 117.6471 | 200
Wholesaler |  | 70% | 69.2042 | 117.6471
Exporter |  | 70% | 40.7083 | 69.2042
Manufacturer |  | 70% | 23.9461 | 40.7083
Cost of the B of M
2 Suppliers |  |  | 23.9461
1 Supplier |  |  | 16.765
Check Problem 8
Solution
Back
Based on the cost point of the Bill of Material (B of M), should the manufacturer opt for one or two suppliers.
The 2x quantity discount is 30%.
Should opt for one supplier.
The unit B of M cost is lower
= $16.77
=$23.95-(23.95*.3)

## 8
Supply Chain | Pays the Node Below | Required % Mark-up
Nodes
Consumer | 200
Retailer |  | 70%
Wholesaler |  | 70%
Exporter |  | 70%
Manufacturer |  | 70%
Cost of the B of M
1 Supplier
2 Suppliers
Problem 8
Back
Based on the cost point of the bill of material, should the manufacturer
opt for one or two suppliers. The 2x quantity discount is 30%.
Check

## Check7
Activity | a | m | b | Variance
A | 2 | 4 | 7 | 0.69444
B | 2 | 6 | 7 | 0.69444
D | 6 | 12 | 12 | 1
F | 6 | 8 | 16 | 2.7778
G | 1 | 5 | 6 | 0.69444
5.8611
Project Variance |  |  |  | 5.8611
Project Standard Deviation |  |  |  | 2.421
z= |  |  |  | 0.34298 | 35 | 34.17
Probability (NORM.S.DIST)= |  |  |  | 0.63307 | 63.31%
Check Problem 7
Solution
Calculate the probability that the project from the previous
problem can be completed in 35 weeks.
Back
Should this project be accepted when the benchmark
threshold for acceptance is 70% of probability of
completion?
Based on the threshold benchmark of 70% this project should not be accepted.
Calculated each variance using the following formula:
((b-a)/6)^2
=
𝑋 ̅=
Calculated in the previous problem
Calculated in the previous problem
Given in this problem
Only the Steps on the Critical Path

## 7
Problem 7
Calculate the probability that the project from the previous
problem can be completed in 35 weeks.
Back
Check

## Check6
[6 empty] | Activity |  | Time Estimates |  |  | Predecessors |  |  |  | Activity | Time Estimates |  |  | Expected Completion Time
[8 empty] | a | m | b | [5 empty] | a | m | b
[6 empty] | A |  | 2 | 4 | 7 | _ |  |  |  | A | 2 | 4 | 7 | 4.1667
[6 empty] | B |  | 2 | 6 | 7 | A , D |  |  |  | B | 2 | 6 | 7 | 5.5
[6 empty] | C |  | 3 | 4 | 6 | D |  |  |  | C | 3 | 4 | 6 | 4.1667
[6 empty] | D |  | 6 | 12 | 12 | A |  |  |  | D | 6 | 12 | 12 | 11
[6 empty] | E |  | 3 | 6 | 12 | D |  |  |  | E | 3 | 6 | 12 | 6.5
[6 empty] | F |  | 6 | 8 | 16 | B , C |  |  |  | F | 6 | 8 | 16 | 9
[6 empty] | G |  | 1 | 5 | 6 | E , F |  |  |  | G | 1 | 5 | 6 | 4.5
| ES | EF
A | 0 | 4.1667 |  |  |  | B | 15.17 | 20.67 | [6 empty] | Activity | Critical Path
4.1667 | 0.0033333 | 4.17 |  |  |  | 5.5 | 15.17 | 20.67 | [7 empty] | LS | ES | Yes
| LS | LF | [12 empty] | A | 0.0033333 | 0 | 0.0033333
| 0.0033333 | [5 empty] | 0 |  |  | F | 20.67 | 29.67 |  |  | B | 15.17 | 15.17 | 0
[10 empty] | 9 | 20.67 | 29.67 |  |  | C | 16.5033 | 15.1667 | 1.3367
[15 empty] | D | 4.17 | 4.1667 | 0.0033333
[11 empty] | 0 |  |  |  | E | 23.17 | 15.1667 | 8.0033
|  | D | 4.1667 | 15.1667 |  | C | 15.1667 | 19.3333 | [6 empty] | F | 20.67 | 20.67 | 0
|  | 11 | 4.17 | 15.17 |  | 4.1667 | 16.5033 | 20.67 | [6 empty] | G | 29.67 | 29.67 | 0
|  |  | 0.0033333 |  |  |  | 1.3367 |  |  |  |  | G | 29.67 | 34.17
[12 empty] | 4.5 | 29.67 | 34.17
|  |  |  | E | 15.1667 | 21.6667 | [6 empty] | 0
|  |  |  | 6.5 | 23.17 | 29.67
8.0033
Check Problem 6
Solution
A project has been defined as shown below.
Calculate the critical path of this project. All time estimates are in weeks.
Back
Activates in red are on the critical path.
Start Point
Calculated Using this formula
(a+4m+b)/6
Answer:
The steps on the critical path are:
A - B - D - F - G
Use this value in the next problem

## 6
Activity | Time Estimates |  |  | Predecessors
| a | m | b
A | 2 | 4 | 7 | _
B | 2 | 6 | 7 | A , D
C | 3 | 4 | 6 | D
D | 6 | 12 | 12 | A
E | 3 | 6 | 12 | D
F | 6 | 8 | 16 | B , C
G | 1 | 5 | 6 | E , F
Problem 6
A project has been defined as shown below.
Calculate the critical path of this project. All time estimates are in weeks.
Back
Check

## Check5
925000
9.25
Check Problem 5
Currently, this part is being produced by outside vendor at the cost of $9.25 per unit. Your firm buys 100,000 units per year from this vendor.
Management wants to bring production of this part "in-house".
The accounting department has advised that additional costs will have to be incurred when the part is manufactured "in-house".
These costs are: fixed, labor, factory overhead, raw materials.
Solution
Back
What is the maximum level of those additional costs ($ for all 100,000 unit) before this move cannot be justified on the economic basis?
The total equivalence cost is =
per unit =
The unit equivalence cost is =

## 5
Problem 5
Back
Check
Currently, this part is being produced by outside vendor at the cost of $9.25 per unit. Your firm buys 100,000 units per year from this vendor.
Management wants to bring production of this part "in-house".
The accounting department has advised that additional costs will have to be incurred when the part is manufactured "in-house".
These costs are: fixed, labor, factory overhead, raw materials.
What is the maximum level of those additional costs ($ for all 100,000 unit) before this move cannot be justified on the economic basis?

## Check4
121
Location | X Coordinate | Y Coordinate | Volume
A | 400 | 150 | 250
B | 450 | 350 | 450
C | 350 | 400 | 350
D | 25 | 450 | 450
1500
X= | 290.8333
Y= | 358.3333
Check Problem 4
The coordinates of each site and the shipment volumes are shown below.
Calculate the coordinates of the optimum location of the new warehouse
needed to serve these locations.
Solution
Back
Sum
= (400*250 + 450*450 + 350*350 + 25*450)/1500
= (150*250 + 350*450 + 400*350 + 450*450)/1500

## 4
Location | X Coordinate | Y Coordinate | Volume
A | 400 | 150 | 250
B | 450 | 350 | 450
C | 350 | 400 | 350
D | 25 | 450 | 450
Problem 4
Back
Check
The coordinates of each site and the shipment volumes are shown below.
Calculate the coordinates of the optimum location of the new warehouse
needed to serve these locations.

## Check3
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 10 | 8 | 6 | 500
Plant X | 16 | 8 | 6 | 600
Plant Y | 18 | 14 | 10 | 600
Warehouse Demand | 600 | 400 | 400
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 500 |  |  | 500
Plant X | 100 | 400 | 100 | 600 | 1700
Plant Y |  |  | 300 | 600
Warehouse Demand | 600 | 400 | 400
|  | 1400 |  |  | 300
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 5000 |  |  | 500
Plant X | 1600 | 3200 | 600 | 600
Plant Y |  |  | 3000 | 600
Warehouse Demand | 600 | 400 | 400
Total Cost | 13400
Check Problem 3
Using the North-west Corner Rule, calculate the approximate
transportation cost given the following information:
Solution
Back
Supply Surplus

## 3
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 10 | 8 | 6 | 500
Plant X | 16 | 8 | 6 | 600
Plant Y | 18 | 14 | 10 | 600
Warehouse Demand | 600 | 400 | 400
121
75
45
25
100
100
Problem 3
Using the North-west Corner Rule, calculate the approximate
transportation cost given the following information:
Back
Check

## Check2
Arc | Distance
1 - 2 | 240
1 - 3 | 160
2 - 3 | 140
2 - 4 | 100
3 - 4 | 180 | 740
3 - 5 | 160
4 - 5 | 160
4 - 6 | 220
5 - 6 | 180
Check Problem 2
Stevenson 477
The following table represents a network with the arcs identified by their
starting and ending nodes. Use the minimal spanning tree method to
find the minimum distance required to connect these nodes.
Solution
Back
1
2
3
4
5
6
240
160
160
140
100
180
160
180
220
160+140+100+160+180 = 740

## 2
Arc | Distance
1 - 2 | 240
1 - 3 | 160
2 - 3 | 140
2 - 4 | 100
3 - 4 | 180
3 - 5 | 160
4 - 5 | 160
4 - 6 | 220
5 - 6 | 180
Problem 2
Stevenson 477
The following table represents a network with the arcs identified by their
starting and ending nodes. Use the minimal spanning tree method to
find the minimum distance required to connect these nodes.
Back
Check

## Check1
Start Point | Distance | End Point
1 | 6 | 2
1 | 4 | 3
2 | 6 | 4
3 | 6 | 5
4 | 2 | 5
4 | 4 | 6
5 | 2 | 7
6 | 4 | 7
6 | 6 | 8
7 | 12 | 8
121
Check Problem 1
Calculate the best way that John can take from Poin1 to Point 8 that
will minimize total distance traveled.
All distances shown are in hundreds of miles.
Solution
Back
1
2
3
4
5
6
7
8
6
4
6
6
2
8
2
4
12
400+600+200+400+600 =2,200
6

## 1.2
Start Point | Distance | End Point
1 | 6 | 2
1 | 4 | 3
2 | 6 | 4
3 | 6 | 5
4 | 2 | 5
4 | 4 | 6
5 | 2 | 7
6 | 4 | 7
6 | 6 | 8
7 | 12 | 8
121
Problem 1
Calculate the best way that John can take from Poin1 to Point 8 that
will minimize total distance traveled.
All distances shown are in hundreds of miles.
Solution
Back
Check

## FirstPage
OM 302
Click Here to Start
Test 3
Sample
4/28/18

## Inquiry Form
Back
OM 302 Test 3
Inquiry Form
Your name: Type here
Class section (Day): type here
Class time: Type here
Problem to be reviewed:
A
Reason:
A
My solution and rationale:
A
Problem to be reviewed:
A
Reason:
A
My solution and rationale:
A
Problem to be reviewed:
A
Reason:
A
My solution and rationale:
A
If you would like me to review any of your test answers please fill this Inquiry Form.
When done, please:
1. Save this file.
2. E-mail the entire file to:
dpodobas@csusm.edu
Problem to be reviewed:
A
Reason:
A
My solution and rationale:
A

## Content Master
OM 302 Test 3
Content
Back
Problem 1
Problem 2
Problem 5
Problem 3
Problem 4
Problem 6
Problem 8
Problem 7
Problem 9
Problem 10