## FirstPage
OM 302 F21
Click Here to Start
Test 3
v.4
12/5/21

## Content Master
Direct mapping
Test Problem | Pretest or Project Management Sample Problems
1 | Pretest 1
2 | Pretest 6
3 | Pretest 3
4 | Pretest 4
5 | Pretest 5
6 | Pretest 8
7 | PM Sample Problems
8 | Pretest 2
9 | Pretest 9
10 | PM Sample Problems
OM 302 Test 3 v.04
Content
Back
Problem 1
Problem 2
Problem 5
Problem 3
Problem 4
Problem 6
Problem 8
Problem 7
Problem 9
Problem 10

## Problem 1d
Problem 1
Back
Pasternak 245
Governments of Hungary, Czech Republic, Slovakia, and Poland are interested in building a highway system similar to the Interstate Highway system of the United States and Autobahn in Germany.
The particular interest in creating this network is to connect the city of Budapest (which is land-locked) with the Polish Baltic port of Gdansk.
There is a set of existing local routes, shown on the next page, that could be expanded and re-designed to link these two cities as an interstate corridor.
Find the shortest path that would make this possible. reason, the preference is that the first leg of that connection links the capital of Hy
All distances are shown in kilometers. What is the shortest distance in kilometers?
Next

## Problem 1
Gdansk
Gdansk
Cieszyn
Budapest
Back
Gdansk
Poznan
Torun
Warsaw
Lodz
Lublin
Wroclaw
Krakow
Prague
Cieszyn
Brno
Kosice
Bratislava
Budapest
361
167
179
195
185
216
233
175
205
293
238
271
276
127
329
308
216
138
300
366
193
362
147
60
Problem 1
Workspace

## Problem 2
Check Problem 2
Back
Problem 2
Back
The BBS firm currently spends $1,200,000 per quarter for 200,000 modules that are needed during a year in production of its final product.
Management wants to bring production of this module "in-house".
The accounting department has advised that additional costs will have to be incurred when the part is manufactured "in-house".
These costs are: fixed, labor, factory overhead, raw materials.
What is the unit equivalency (indifference) cost?
Meaning, at what price point it does not matter where this part is sourced from.
Workspace

## Problem 3
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 12 | 10 | 7 | 350
Plant X | 20 | 9 | 6 | 500
Plant Y | 18 | 10 | 10 | 300
Warehouse Demand | 400 | 600 | 200
Problem 3
Back
a) Using the North-west Corner Rule, calculate the approximate
transportation cost given the following information.
b) Is this problem balanced or unbalanced?
c) What is the surplus or deficit, if any?
Inside the table are costs to ship one unit.
Workspace

## Problem 4
Location | X Coordinate | Y Coordinate | Volume
A | 700 | 150 | 350
B | 450 | 350 | 800
C | 350 | 400 | 700
D | 25 | 450 | 400
Problem 4
Back
The coordinates of each site and the shipment volumes are shown below.
Calculate the coordinates of the optimum location of the new warehouse
needed to serve these locations. Use the Center of Gravity method.
Select the x and y coordinates.
Workspace

## Problem 5
Activity | Time Estimates |  |  | Predecessors
| a | m | b
A | 2 | 4 | 7 | _
B | 2 | 6 | 7 | A , D
C | 3 | 4 | 6 | D
D | 6 | 12 | 12 | A
E | 3 | 6 | 12 | D
F | 6 | 8 | 16 | B , C
G | 2 | 8 | 9 | E , F
`
Problem 5
Back
Calculate the expected completion time for activity G.
Workspace

## Problem 6
Score (scale: 0 to 10)
Criterion | Weight | Vendor A | Vendor B | Vendor C
Total Cost | 25 | 5 | 8 | 9
On-time Delivery | 30 | 9 | 6 | 7
Consistent Quality | 30 | 8 | 9 | 6
Environment | 15 | 9 | 6 | 8
Problem 6
Back
Workspace
Krajewski 363
Three international vendors are under consideration. The preference matrix is shown below.
a) Which vendor should be selected?
b) What is the score for this vendor?

## Problem 7
Activity | Earliest Start (ES) | Latest Start (LS) | Earliest Finish (EF) | Latest Finish (LF) | Slack | Critical Path | Optimistic, Most probable, and pessimistic Activity time Estimates (in Weeks)
(LS-ES)
A | 0 | 0 | 6 | 6 | 0 |  | Activity | Optimistic (a) | Most Probable (m) | Pessimistic (b)
B | 0 | 7 | 2 | 9 | 7 |  | A | 4 | 7 | 12
C | 6 | 10 | 9 | 13 | 4 |  | B | 1 | 2 | 5
D | 6 | 7 | 11 | 12 | 1 |  | C | 2 | 4 | 7
E | 6 | 6 | 9 | 9 | 0 |  | D | 3 | 5 | 11
F | 9 | 13 | 11 | 15 | 4 |  | E | 2 | 4 | 6
G | 11 | 12 | 14 | 15 | 1 |  | F | 1.5 | 3 | 5
H | 9 | 9 | 13 | 13 | 0 |  | G | 1.5 | 4 | 4.5
I | 13 | 13 | 15 | 15 | 0 |  | H | 2.5 | 4 | 7.5
J | 15 | 15 | 17 | 17 | 0 |  | I | 1.5 | 3 | 3.5
[7 empty] | J | 1 | 2 | 3
Back
Problem 7
What is the probability of completing this project within 20 days?
Workspace

## Problem 8
Arcs between Nodes | Distance
1 - 2 | 320
1 - 3 | 100
1 - 4 | 200
2 - 4 | 80
3 - 4 | 100
3 - 5 | 120
4 - 5 | 120
4 - 6 | 200
5 - 6 | 75
Problem 8
Back
Workspace
Stevenson 477
The following table represents a network with the arcs identified by their starting and ending nodes.
Use the minimal spanning tree method to find the minimum distance required to connect these nodes. Hint: draw a network diagram first.

## Problem 9
Supply Chain | Pays the Node Below | Required % Mark-up | Buys for | Sells for
Nodes
Consumer | 400
Retailer |  | 80%
Wholesaler |  | 80%
Exporter |  | 80%
Manufacturer |  | 70%
Cost of the B of M
2 Suppliers
1 Supplier
Problem 9
Back
a) Based on the cost point of the Bill of Material (B of M), should a manufacturer opt for one or two suppliers. The lower cost wins.
The 2x quantity discount is 30%.
b) How much should this manufacturer pay for parts from this supplier(s)?

## Problem 10
Activity | Duration | Predecessors
A | 3 | _
B | 4 | _
C | 2 | A
D | 4 | B
E | 4 | C
F | 3 | C
G | 5 | C , D , E
H | 3 | F , G
Problem 10
Back
Calculate the expected project completion time (in weeks) using a Gantt chart.
Workspace
Weeks:
American Standard: First day of the week is Sunday
International Standard: First day of the week is Monday

## Table
Current Gross Margin (%)
Sales Increase Needed to Earn Some Gross Margin (%) as Before Price Cut
|  | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50%
Expected Price Cut | 1% | 25% | 11.1% | 7.1% | 5.3% | 4.2% | 3.4% | 2.9% | 2.6% | 2.3% | 2%
| 2% | 66.6% | 25% | 15.4% | 11.1% | 8.7% | 7.1% | 6.1% | 5.3% | 4.7% | 4.2%
| 3% | 150% | 42.8% | 25% | 17.6% | 13.6% | 11.1% | 9.4% | 8.1% | 7.1% | 6.4%
| 4% | 400% | 66.6% | 36.4% | 25% | 19% | 15.4% | 12.9% | 11.1% | 9.8% | 8.7% |  | 50
| 5% |  | 100% | 50% | 33.3% | 25% | 20% | 16.7% | 14.3% | 12.5% | 11.1%
| 6% |  | 150% | 66.7% | 42.9% | 31.6% | 25% | 20.7% | 17.6% | 15.4% | 13.6% |  | 10
| 7% |  | 233.3% | 87.5% | 53.8% | 38.9% | 30.4% | 25% | 21.2% | 18.5% | 16.3%
| 8% |  | 400% | 114.3% | 66.7% | 47.1% | 36.4% | 29.6% | 25% | 21.6% | 19%
| 9% |  | 1000% | 150% | 81.8% | 56.3% | 42.9% | 34.6% | 29% | 25% | 22% |  | 20000
| 10% |  |  | 200% | 100% | 66.7% | 50% | 40% | 33.3% | 28.6% | 25%
| 11% |  |  | 275% | 122.2% | 78.6% | 57.9% | 45.8% | 37.9% | 32.4% | 28.2%
| 12% |  |  | 400% | 150% | 92.3% | 66.7% | 52.2% | 42.9% | 36.4% | 31.6% | 5000
| 13% |  |  | 650% | 185.7% | 108.3% | 76.5% | 59.1% | 48.1% | 40.7% | 35.1%
| 14% |  |  | 1400% | 233.3% | 127.3% | 87.5% | 66.7% | 53.8% | 45.2% | 38.9%
| 15% |  |  |  | 300% | 150% | 100% | 75% | 60% | 50% | 42.9%
| 16% |  |  |  | 400% | 177.8% | 114.3% | 84.2% | 66.7% | 55.2% | 47.1%
| 17% |  |  |  | 566.7% | 212.5% | 130.8% | 94.4% | 73.9% | 60.7% | 52.6%
| 18% |  |  |  | 900% | 257.1% | 150% | 105.9% | 81.8% | 66.7% | 56.3%
| 19% |  |  |  | 1900% | 316.7% | 172.7% | 118.8% | 90.5% | 70.1% | 61.3%
| 20% |  |  |  |  | 400% | 200% | 133.3% | 100% | 80% | 66.7%
| 21% |  |  |  |  | 525% | 233.3% | 150% | 110.5% | 87.7% | 72.5%
| 22% |  |  |  |  | 733.3% | 275% | 169.2% | 122.2% | 95.7% | 78.7%
| 23% |  |  |  |  | 1115% | 328.6% | 191.7% | 135.3% | 104.6% | 85.5%
| 24% |  |  |  |  | 2400% | 400% | 218.2% | 150% | 114.3% | 92.6%
| 25% | Sales Increase Needed to Earn Some Gross Margin (%) as Before Price Cut 30%: 500%; Sales Increase Needed to Earn Some Gross Margin (%) as Before Price Cut 35%: 250%; Sales Increase Needed to Earn Some Gross Margin (%) as Before Price Cut 40%: 166.7%; Sales Increase Needed to Earn Some Gross Margin (%) as Before Price Cut 45%: 125%; Sales Increase Needed to Earn Some Gross Margin (%) as Before Price Cut 50%: 100%
At intersection of price cut row and current gross profit column find percentage increase in unit sales required to maintain the same absolute gross profit as before the price cut.
Back
This table was constructed using the following formula: