## Check10
Activity | Duration | Predecessors | Activity
A
A | 2 | _ | B
B | 3 | _ | C
C | 2 | A | D
D | 4 | B | E
E | 4 | C | F
F | 3 | C | G
G | 5 | D , E | H
H | 2 | F , G
|  |  | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Check Problem 10
Calculate the expected project completion time (in weeks) using a Gantt chart.
Solution
Back
The duration of this project is 15 weeks.
Time Related Standards:
Dates:
American Standard: 4/19/17
Standard: 19/4/17
International Standard: 2017/4/19
Weeks:
American Standard: First day of the week is Sunday
International Standard: First day of the week is Monday

## 10
Activity | Duration | Predecessors
A | 2 | _
B | 3 | _
C | 2 | A
D | 4 | B
E | 4 | C
F | 3 | C
G | 5 | D , E
H | 2 | F , G
Problem 10
Calculate the expected project completion time (in weeks) using a Gantt chart.
Solution
Back
Check

## Check9
200040
150000
50040
Check Problem 9
You are a Product Manager for your company. Your VP of Sales requested that you drop the price for your product by 20%. This is necessary, according to your VP, to combat a new competitor entering your market.
The long standing policy of your firm is that any price reductions have to be Gross Profit ($) neutral. In other words, they cannot affect the $ value of the Gross Profit.
The current Gross Margin is 50%. Gross Margin = (Revenue - Cost of Goods Sold)/Revenue
The most recent market research shows that your company has 50% market share. The remaining share is equally divided between two other competitors. It also estimates that the market for your products grows at the rate of 10% per year.
Currently, your manufacturing plant works at 80% of capacity. That is, it produces 120,000 units per year. All units that are produced are sold.
Should you comply with your VPs request? Why or why not? Support your answer using numerical values.
Solution
Back
From the table: the required increase in unit sales is 66.7%.
The company has to sell 200,040 units to justify the proposed price drop.
The total production capacity is 150,000 units at 100% utilization.
Table
=120,000 + (120,000 *0.667)
The company does not have enough production capacity to justify this drop in unit price. There is a need to produce additional
50,400 units.
From the problem
200,040 - 150,000 = 50,040

## Table
Current Gross Profit
Sales Increase Needed to Earn Some Gross Profit as Before Price Cut
|  | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50%
Expected Price Cut | 1% | 25% | 11.1% | 7.1% | 5.3% | 4.2% | 3.4% | 2.9% | 2.6% | 2.3% | 2%
| 2% | 66.6% | 25% | 15.4% | 11.1% | 8.7% | 7.1% | 6.1% | 5.3% | 4.7% | 4.2%
| 3% | 150% | 42.8% | 25% | 17.6% | 13.6% | 11.1% | 9.4% | 8.1% | 7.1% | 6.4%
| 4% | 400% | 66.6% | 36.4% | 25% | 19% | 15.4% | 12.9% | 11.1% | 9.8% | 8.7% | GP (%) |  | 50
| 5% |  | 100% | 50% | 33.3% | 25% | 20% | 16.7% | 14.3% | 12.5% | 11.1%
| 6% |  | 150% | 66.7% | 42.9% | 31.6% | 25% | 20.7% | 17.6% | 15.4% | 13.6% | Price Change (%) |  | 10
| 7% |  | 233.3% | 87.5% | 53.8% | 38.9% | 30.4% | 25% | 21.2% | 18.5% | 16.3%
| 8% |  | 400% | 114.3% | 66.7% | 47.1% | 36.4% | 29.6% | 25% | 21.6% | 19%
| 9% |  | 1000% | 150% | 81.8% | 56.3% | 42.9% | 34.6% | 29% | 25% | 22% | Current Sales (units) |  | 20000
| 10% |  |  | 200% | 100% | 66.7% | 50% | 40% | 33.3% | 28.6% | 25%
| 11% |  |  | 275% | 122.2% | 78.6% | 57.9% | 45.8% | 37.9% | 32.4% | 28.2% | Needed Sales (units)
| 12% |  |  | 400% | 150% | 92.3% | 66.7% | 52.2% | 42.9% | 36.4% | 31.6% | #DIV/0! | 5000
| 13% |  |  | 650% | 185.7% | 108.3% | 76.5% | 59.1% | 48.1% | 40.7% | 35.1%
| 14% |  |  | 1400% | 233.3% | 127.3% | 87.5% | 66.7% | 53.8% | 45.2% | 38.9%
| 15% |  |  |  | 300% | 150% | 100% | 75% | 60% | 50% | 42.9%
| 16% |  |  |  | 400% | 177.8% | 114.3% | 84.2% | 66.7% | 55.2% | 47.1%
| 17% |  |  |  | 566.7% | 212.5% | 130.8% | 94.4% | 73.9% | 60.7% | 52.6%
| 18% |  |  |  | 900% | 257.1% | 150% | 105.9% | 81.8% | 66.7% | 56.3%
| 19% |  |  |  | 1900% | 316.7% | 172.7% | 118.8% | 90.5% | 70.1% | 61.3%
| 20% |  |  |  |  | 400% | 200% | 133.3% | 100% | 80% | 66.7%
| 21% |  |  |  |  | 525% | 233.3% | 150% | 110.5% | 87.7% | 72.5%
| 22% |  |  |  |  | 733.3% | 275% | 169.2% | 122.2% | 95.7% | 78.7%
| 23% |  |  |  |  | 1115% | 328.6% | 191.7% | 135.3% | 104.6% | 85.5%
| 24% |  |  |  |  | 2400% | 400% | 218.2% | 150% | 114.3% | 92.6%
| 25% | Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 30%: 500%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 35%: 250%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 40%: 166.7%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 45%: 125%; Sales Increase Needed to Earn Some Gross Profit as Before Price Cut 50%: 100%
At intersection of price cut row and current gross profit column find percentage increase in unit sales required to maintain the same absolute gross profit as before the price cut.
Back
66.7% more units will have to be sold in order to maintain the current level of Gross Profit.

## 9
Problem 9
You are a Product Manager for your company. Your VP of Sales requested that you drop the price for your product by 20%. This is necessary, according to your VP, to combat a new competitor entering your market.
The long standing policy of your firm is that any price reductions have to be Gross Margin neutral. In other words, they cannot affect the $ value of the Gross Margin.
The current Gross Margin is 50%. Gross margin = Revenue - Cost of Goods Sold
The most recent market research shows that your company has 50% market share. The remaining share is equally divided between two other competitors. It also estimates that the market for your products grows at the rate of 10% per year.
Currently, your manufacturing plant works at 80% of capacity. That is, it produces 120,000 units per year. All units that are produced are sold.
Should you comply with your VPs request? Why or why not? Support your answer using numerical values.
Solution
Back
Check

## Check8
Supply Chain
|  | Consumer Pays Retailer | 100
Required % Mark-up
Retailer | 50% | Retailer Pays Wholesaler | 66.6667
Wholesaler | 50% | Wholesaler pays Exporter | 44.4444
Exporter | 50% | Exporter pays Manufacturer | 29.6296
Manufacturer | 50% | Manufacturer pays Suppliers | 19.7531
Cost of the B of M
2 Suppliers | Half the volume each |  | 19.7531
1 Supplier | Entire volume |  | 15.8025
Check Problem 8
Solution
Back
Based on the cost point of the bill of material, should the manufacturer opt for one or two suppliers.
The 2x quantity discount is 20%. Show your calculations.
Should opt for one supplier.
$19.75*. 8 = $15.80
$100 = cost+cost*.5
$100 = 1.5 cost
cost = $100/1.5
cost = $66.67
The difference between $19.75 and $15.80
can increase profitability

## 8
Supply Chain | Pays the Node Below | Required % Mark-up
Nodes
Consumer | 100
Retailer |  | 50%
Wholesaler |  | 50%
Exporter |  | 50%
Manufacturer |  | 50%
Cost of the B of M
2 Suppliers
1 Supplier
Problem 8
Solution
Back
Based on the cost point of the bill of material, should the manufacturer
opt for one or two suppliers. The 2x quantity discount is 20%.
Check

## Check7
Activity on the Critical Path
| a | m | b | Activity Variance
A | 1 | 4 | 7 | 1
C | 3 | 4 | 6 | 0.25
D | 6 | 12 | 14 | 1.7778 | 6.5
F | 6 | 8 | 16 | 2.7778
G | 1 | 5 | 6 | 0.69444
Project Variance |  |  |  | 6.5
Project Standard Deviation |  |  |  | 2.5495
z = (34-33)/2.55 |  |  |  | 0.39216
Probability (NORM.S.DIST)= |  |  |  | 65.25%
Check Problem 7
Solution
Calculate the probability that the project from the previous
problem can be completed in 34 weeks.
The expected completion time is 33 weeks.
If the threshold for acceptance is 70% would you proceed with this project?
Back
The project should not be proceeded.
The threshold for acceptence is 70%
= Sum of activity variances
=
=√(2&6.50)
=1 + 0.25 + 1.78 + 2.78 + 0.69
=(
=(〖(𝑏−𝑎):6)〗^2

## 7
Activity | a | m | b
A | 1 | 4 | 7
C | 3 | 4 | 6
D | 6 | 12 | 14
F | 6 | 8 | 16
G | 1 | 5 | 6
Problem 7
Solution
Calculate the probability that the project from the previous
problem can be completed in 34 weeks.
The expected completion time is 33 weeks.
If the threshold for acceptance is 70% would you proceed with this project?
The activities on the critical path are shown below.
Back
Check

## Check6
Activity Expected Completion Time
Activity | Time Estimates
| a | m | b
A | 1 | 4 | 7 | 4
B | 2 | 6 | 7 | 5.5
C | 3 | 4 | 6 | 4.1667
D | 6 | 12 | 14 | 11.3333
E | 3 | 6 | 12 | 6.5
F | 6 | 8 | 16 | 9
G | 1 | 5 | 6 | 4.5
Activity | Time Estimates |  |  | Predecessors
| a | m | b
A | 1 | 4 | 7 | _
B | 2 | 6 | 7 | A
C | 3 | 4 | 6 | A, D
D | 6 | 12 | 14 | A
E | 3 | 6 | 12 | D
F | 6 | 8 | 16 | B , C
G | 1 | 5 | 6 | E , F | [7 empty] | A | ES | EF
[12 empty] | ECT | LS | LF
| ES | EF | [5 empty] | ES | EF
A | 0 | 4 |  |  |  |  | B | 4 | 9.5
4 | 0 | 4 |  |  |  |  | 5.5 | 14 | 19.5
| LS | LF | [5 empty] | LS | LF |  |  |  |  | ES | EF
[13 empty] | F | 19.5 | 28.5
[13 empty] | 9 | 19.5 | 28.5
[14 empty] | LS | LF
[6 empty] | ES | EF |  |  | ES | EF
[5 empty] | D | 4 | 15.3333 |  | C | 15.3333 | 19.5
[5 empty] | 11.3333 | 4 | 15.3333 |  | 4.1667 | 15.3333 | 19.5
[6 empty] | LS | LF |  |  | LS | LF |  |  | ES | EF
[13 empty] | G | 28.5 | 33
[13 empty] | 4.5 | 28.5 | 33
[8 empty] | ES | EF |  |  |  |  | LS | LF
[7 empty] | E | 15.3333 | 21.8333
[7 empty] | 6.5 | 22 | 28.5
[8 empty] | LS | LF
Activity | Critical Path
| LS | ES | Yes
A | 0 | 0 | 0
B | 14 | 4 | 10
C | 15.3333 | 15.3333 | 0
D | 4 | 4 | 0
E | 22 | 15.3333 | 6.6667
F | 19.5 | 19.5 | 0
G | 28.5 | 28.5 | 0
Check Problem 6
Solution
A project has been defined as shown below.
Calculate the critical path of this project.
All time estimates are in weeks.
Back
Activates in red are on the critical path.
Use this formula for each activity to calculate the ECT:
Step 1.
Calculate the Activity Expected Completion Time
Step 2.
Draw the network diagram. Use the predecessors.
Step 3.
Complete the forward pass (all ES and EF) and backward pass (all LS and LF)
Step 4.
Identify steps that are on the critical path (in red)
Subtract ES from LS to calculate the slack of each activity
(copy from EF to LF)
=
=𝑋 ̅
Key
ECT - Expected Completion Time
ES - Earliest Start
EF - Earliest Finish
LS - Latest Start
LF - Latest Finish
=
= (𝑎+4𝑚+𝑏)/6
Forward Pass
(use the latest EF)
EF = ECT + ES
Last Activity G: LF = EF
LS = LF - ECT
Backward Pass
(use the earliest LS)
Reference Key

## 6
Activity | Time Estimates |  |  | Predecessors
| a | m | b
A | 1 | 4 | 7 | _
B | 2 | 6 | 7 | A
C | 3 | 4 | 6 | A, D
D | 6 | 12 | 14 | A
E | 3 | 6 | 12 | D
F | 6 | 8 | 16 | B , C
G | 1 | 5 | 6 | E , F
Problem 6
Solution
A project has been defined as shown below.
Calculate the critical path of this project. All time estimates are in weeks.
Back
Check

## Check5
835000
8.35 | vs. | 8.25
Check Problem 5
The engineering department believes that it might be possible to cut costs by bringing back manufacturing of one of the parts in house. Currently, this part is being produced by outside vendor at the cost of $8.25 per unit.
Your firm buys 100,000 units per year. The accounting department complied the following list of costs that your firm will incur when the part is manufactured in-house:
Fixed costs will increase by $50,000.
Labor costs will increase by $125,000
Factory overhead currently running at $500,000 per year, will increase by 12% per year.
Raw materials used to make this part (100,000 units) will cost $600,000.
Solution
Back
Should this firm make or buy this part?
The total cost incurred if the parts were manufactured in house:
Additional fixed cost: $50,000
Additional labor cost: $125,000
Raw material cost: $600,000
Additional Overhead: $500,000 x 0.12 = 60,000
Total cost: $835,000
The cost per unit: $835,000/100,000 = $8.35
It is less expensive to buy parts for this vendor.

## 5
Problem 5
The engineering department believes that it might be possible to cut costs by bringing back manufacturing of one of the parts in house. Currently, this part is being produced by outside vendor at the cost of $8.25 per unit.
Your firm buys 100,000 units per year. The accounting department complied the following list of costs that your firm will incur when the part is manufactured in-house:
Fixed costs will increase by $50,000.
Labor costs will increase by $125,000
Factory overhead currently running at $500,000 per year, will increase by 12% per year.
Raw materials used to make this part (100,000 units) will cost $600,000.
Solution
Back
Should this firm make or buy this part?
Check

## Check4
121
2000
1
Location | Function | X Coordinate | Y Coordinate | Volume
Anaheim (A) | Distributor | 400 | 150 | 250
La Habra (L) | Distributor | 450 | 350 | 450
Glendale (G) | Distributor | 350 | 400 | 350 | 1500
Thousand Oaks (T) | Distributor | 25 | 450 | 450 |  | 75
[6 empty] | 45 | 37
[6 empty] | 25 | 43
[6 empty] | 100 | 61
X = | 290.8333 |  |  |  |  | 100 | 30
Y = | 358.3333
Check Problem 4
The Hi Octane Refining Company needs to locate an intermediate holding
facility between its refining plant in Long Beach and its major distributors.
The coordinates of each site and the shipment volumes from the Long Beach refinery to each distributor are shown below.
Calculate the coordinates of the optimum location of this new facility.
Solution
Back
250 + 450 + 350 + 450 = 1500
= ((400*250)+(450*450)+(350*350)+(25*450))/1500
= ((150*250)+(350*450)+(350*350)+(450*450))/1500

## 4
121
2000
1
Location | Function | X Coordinate | Y Coordinate | Volume
Anaheim | Distributor | 400 | 150 | 250
La Habra | Distributor | 450 | 350 | 450
Glendale | Distributor | 350 | 400 | 350
Thousand Oaks | Distributor | 25 | 450 | 450 | 75
[5 empty] | 45 | 37
[5 empty] | 25 | 43
[5 empty] | 100 | 61
[5 empty] | 100 | 30
Problem 4
The Hi Octane Refining Company needs to locate an intermediate holding
facility between its refining plant in Long Beach and its major distributors.
The coordinates of each site and the shipment volumes from the Long Beach refinery to each distributor are shown below.
Calculate the coordinates of the optimum location of this new facility.
Solution
Back
Check

## Check3
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 5 | 4 | 3 | 250
Plant X | 8 | 4 | 3 | 300
Plant Y | 9 | 7 | 5 | 300
Warehouse Demand | 300 | 200 | 200
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 250 |  |  | 250
Plant X | 50 | 200 | 50 | 300 | 850
Plant Y |  |  | 150 | 300
Warehouse Demand | 300 | 200 | 200
|  | 700 |  |  | 150
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 1250 |  |  | 250
Plant X | 400 | 800 | 150 | 300
Plant Y |  |  | 750 | 300 |  | 75
Warehouse Demand | 300 | 200 | 200 |  |  | 45
25
100
100
Total Cost | 3350
Check Problem 3
Using the North-west Corner Rule, calculate the approximate
transportation cost given the following information:
Solution
Back
Supply Surplus

## 3
| Warehouse A | Warehouse B | Warehouse C | Plant Supply
Plant W | 5 | 4 | 3 | 250
Plant X | 8 | 4 | 3 | 300
Plant Y | 9 | 7 | 5 | 300
Warehouse Demand | 300 | 200 | 200
121
75
45
25
100
100
Problem 3
Using the North-west Corner Rule, calculate the approximate
transportation cost given the following information:
Solution
Back
Check

## Check2
Arc | Distance
1 - 2 | 12
1 - 3 | 8
2 - 3 | 7
2 - 4 | 10
3 - 4 | 9
3 - 5 | 8
4 - 5 | 8
4 - 6 | 11
5 - 6 | 9
Check Problem 2
Stevenson 477
The following table represents a network with the arcs identified by their
starting and ending nodes. Use the minimal spanning tree method to
find the minimum distance required to connect these nodes.
Solution
Back
1
2
3
4
5
6
12
8
8
7
10
9
8
9
11
8+7+8+8+9 = 40

## 2
Arc | Distance
1 - 2 | 12
1 - 3 | 8
2 - 3 | 7
2 - 4 | 10
3 - 4 | 9
3 - 5 | 8
4 - 5 | 8
4 - 6 | 11
5 - 6 | 9
Problem 2
Stevenson 477
The following table represents a network with the arcs identified by
their starting and ending nodes. Use the minimal spanning tree
method to find the minimum distance required to connect these
nodes.
Solution
Back
Check

## Check1
Start Point | End Point | Distance
1 | 2 | 3
1 | 3 | 2
2 | 4 | 3
3 | 5 | 3
4 | 5 | 1
4 | 6 | 4
5 | 7 | 1
6 | 7 | 2
6 | 8 | 3
7 | 8 | 6
121
Check Problem 1
Calculate the best way that John can take from Point1 to Point 8 that
will minimize total distance traveled.
All distances shown are in hundreds of miles.
Solution
Back
1
2
3
4
5
6
7
8
3
2
3
3
1
4
1
2
6
200+300+100+200+300 =1,100
3

## 1
Start Point | End Point | Distance
1 | 2 | 3
1 | 3 | 2
2 | 4 | 3
3 | 5 | 3
4 | 5 | 1
4 | 6 | 4
5 | 7 | 1
6 | 7 | 2
6 | 8 | 3
7 | 8 | 6
121
Problem 1
Calculate the best way that John can take from Point 1 to Point 8 that
will minimize total distance traveled.
All distances shown are in hundreds of miles.
Solution
Back
Check

## FirstPage
DEN 423
Click Here to Start
RPP-Do not duplicate
Sample Problems
11/30/17
Set 3

## Content Master
Content
Back
Problem 1
Problem 2
Problem 5
Problem 3
Problem 4
Problem 6
Problem 8
Problem 7
Problem 9
Problem 10